## Slide 1
Project:
Cafeteria Management
System
Group:
T-RISE

## Slide 2
In this presentation
~ Recap on last demo
~ Progress since last demo
~ Enhancements since last demo
~ Next sprints
~ Current scrum board
~ Current burndown charts

## Slide 3
Recap on last demo
~ Agile- scrum method
~ Sprints – 7 phases (4/7 complete)
~ Client meetings
~ Project management tools (waffle.io and burndown.io)
~ Scrum board
~ Burndown Charts
~ Technologies (MEANJS, Bootstrap, grunt, Moca, npm)
~ Unit testing and showed unit testing for
completed phases
~ Demo of the CMS

## Slide 4
Progress since last meeting
~ Phase 3 now complete (5/7 phases)
~ This includes:
Placing an order :
- when an order is ready cashier will
mark it as done and trigger an e-mail
notification
- Option for users to pay cash or have
it deducted from their salary
- Documentation updated

## Slide 5
Enhancements
~ Security features
~ Working on a dynamic Menu category bar with
dynamic pages
~ When placing an order user can add preferences
~ Available spending credit now appears on
profile page
~ Inefficient funds exception
~ Orders are now numbered
~ For screen utilization menu bar will become
dropdown instead of a breadcrumb

## Slide 6
Next Sprints
~ Phase 4 – Reporting
~ ReportingJS
- Generating bills (pdf)
- Gathering user and system history
(security and auditibility)
- Use history data to create
usage graphs to cafeteria manager
~ Usability testing
~ Start working on maintainability (color
configuration)

## Slide 7
Next Sprints
~ Phase 5 – Pulling together strings
~ This phase will consist of fixing the last
few things of core requirements
~ Nice to haves phase
~ This phase will consist of implementing
nice to have features

## Slide 8
This can be viewed on project README on GitHub repo
Scrum Board

## Slide 9
Burndown Chart
Phase 3 – 87% completed:
This can be viewed on project README on GitHub repo
Phase 4: next phase

## Slide 10
Demo CMS